## Scenario & Weights
M6.6 ¦ Scenario-weighted financial lens
All M6.2 numbers are modeled API billings, not actual revenue. Weights below are purely illustrative judgment calls.
Scenario | Year-1 API billings ($) | Year-1 after-referral-fee ($) | Illustrative weight | Weighted API billings ($) | Weighted after-fee ($) | Source | Evidence grade
Conservative | 1523.9882 | 1516.3683 | 60% | 914.3929 | 909.821 | M6.2 Executive Summary | Unverified scenario
Base | 125411.9363 | 123154.5215 | 35% | 43894.1777 | 43104.0825 | M6.2 Executive Summary | Unverified scenario
Expansion | 2384434.0666 | 2289056.7039 | 5% | 119221.7033 | 114452.8352 | M6.2 Executive Summary | Unverified scenario
ILLUSTRATIVE WEIGHTED TOTAL |  |  | 100% | 164030.274 | 158466.7387
Weight validation |  |  | PASS
Stress setting | Value | Reason / source
Realized workflow volume factor | 75% | Illustrative downside to M6.2 base forecast
Realized negotiated price factor | 90% | Illustrative additional realization sensitivity
Base year-1 API billings ($) | 125411.9363
Downside-stressed base billings ($) | 84653.057
Billings difference ($) | -40758.8793
Use either a weighted scenario view OR an explicit downside case for decisions. Do not stack risk factors on top of already-downside inputs without confirming they are independent.

## Revenue Sensitivity
Revenue sensitivity ¦ What moves the business case
M6.2 base first-year API billings are stressed by independent changes in workflow volume and price realization.
M6.2 base year-1 API billings ($) | 125411.9363
Volume factor × price factor |  | 60% | 75% | 90% | 100% | 120%
| 50% | 37623.5809 | 47029.4761 | 56435.3714 | 62705.9682 | 75247.1618
| 75% | 56435.3714 | 70544.2142 | 84653.057 | 94058.9523 | 112870.7427
| 100% | 75247.1618 | 94058.9523 | 112870.7427 | 125411.9363 | 150494.3236
| 125% | 94058.9523 | 117573.6903 | 141088.4284 | 156764.9204 | 188117.9045
| 150% | 112870.7427 | 141088.4284 | 169306.1141 | 188117.9045 | 225741.4854
A 25% shortfall in workflows and a 10% reduction in realized API pricing produce a different result from the published base case. This sensitivity is not a predictive demand distribution.
Month-12 base paying ISVs | 50
Base Month-12 annualized API billings ($) | 268849.0035
Target annualized API billings ($) | 1000000
Required base-equivalent ISVs | 186
Required monthly workflow volume | 5580000
M6.2 base includes 30,000 monthly workflows per ISV at Month 12. 186 ISVs is a scale equivalence, not validated market penetration or a sales forecast.

## Pilot Capacity
90-day exploratory capacity ¦ Allocation, not authorization
Editable staff-time and fully loaded cost *hypotheses*; Anthropic finance must replace every assumed rate.
Workstream | FTE fraction | Months | Illustrative loaded cost / FTE-month ($) | Modeled 90-day resource cost ($) | Evidence to deliver | Owner confirmed? | Rate status
Product / market discovery | 0.5 | 3 | 30000 | 45000 | External buyer/developer research | No | Illustrative only
Developer relations / ISV | 0.5 | 3 | 25000 | 37500 | Developer onboarding and workflow validation | No | Illustrative only
Solutions / evaluation eng. | 0.25 | 3 | 30000 | 22500 | Paired benchmark and platform fit | No | Illustrative only
Privacy / enterprise review | 0.25 | 3 | 35000 | 26250 | BAA, channel and data-flow gate | No | Illustrative only
Incremental API / test spend ($) |  |  | 5000
Estimated capacity envelope ($) |  |  |  | 136250
FTE-month equivalents |  |  |  | 4.5
Authorization status |  |  |  | NOT AUTHORIZED
Decision | Requested authorization | Not authorized
0–90 day validation | Bounded exploration / capacity review | Large integration build or commercial launch
90–180 day expansion | Only if gates pass | Production PHI without approvals

## Risk Register
Risk-adjusted investment decision ¦ Eight material risks
Scores are analyst judgments; likelihood is not a measured event probability.
Risk | Primary exposure | Likelihood (1-5) | Impact (1-5) | Risk priority | Mitigation / evidence | Stop or escalation trigger | Status
No external buyer demand | Revenue / product-market fit | 4 | 5 | 20 | 6–8 discovery interviews, named sponsor | No credible buyer / workflow sponsor after outreach | Unvalidated
Low recurring token volume | Growth / monetization | 4 | 5 | 20 | Observe volume and total cost per accepted workflow | No sustainable usage at customer ROI | Unvalidated
Incumbent AI differentiation | Competitive | 4 | 4 | 16 | Blind matched eval against GPT/Gemini/no-AI | No differentiation or inferior safety/cost | Unvalidated
Clinical safety / intended use | Patient risk / regulatory | 3 | 5 | 15 | High-severity eval, clinician signoff, intended-use review | Any unresolved high-severity failure | Unvalidated
PHI + cloud channel eligibility | Legal / data processing | 4 | 5 | 20 | Validate BAA, service/operator, tools and subprocessors | No approved end-to-end PHI architecture | Unvalidated
Partner/distribution dependency | GTM / control | 3 | 4 | 12 | Direct API first, assess channel after demand | Exclusive access or unexpected channel costs | Unvalidated
Billing / revenue attribution | Financial controls | 3 | 4 | 12 | Actual event reconciliation before live billing | Unexplained metering/settlement discrepancies | Unvalidated
Unvalidated internal economics | Investment efficiency | 4 | 4 | 16 | Finance-owned inference and loaded cost model | Negative contribution at observed workloads | Unvalidated

## Investment Gates
Gated executive decision ¦ GO / ITERATE / STOP
Day 90 can validate whether to fund a controlled pilot; paid production conversion belongs at Day 180 or later.
Gate | Proposed evidence threshold | GO | ITERATE | STOP | Owner | Evidence status | Decision
Buyer / developer demand | At least 6–8 interviews, 2 specific frequent workflows with documented buyer/sponsor | Real sponsor and recurring problem | Promising but workflow/buyer unclear | No validated sponsor or ROI | GTM / PM | Not yet observed | Pending
Matched model evaluation | Blinded current-model + no-AI comparator; predefined clinically reviewed error, traceability and review-time metrics | Acceptable error and differentiated ROI | Some quality/cost questions remain | Unacceptable serious error or no value | Evaluation / Clinical | Not yet observed | Pending
Economics | Observed tokens, clinician minutes and workflow volumes; internal servicing cost where available | Attractive ROI and plausible recurring use | Need narrower use case or pricing | Structurally uneconomic at realistic usage | PM / Finance | Not yet observed | Pending
Enterprise deployment | Actual channel/operator/BAA/feature coverage, data flows and safety scope reviewed | Approved architecture for planned test | Only synthetic data until approvals | PHI handling blocked / unacceptable risk | Security / Legal | Not yet observed | Pending
Partner commercialization | Defined direct/cloud accounting without duplicate billings; no unapproved resell terms | Clear accountable buyer and route | Procurement route pending | Channel cannot support target customer | Partnerships | Not yet observed | Pending
Day-180 production proof | Real paid non-test consumption, retention measured in mature cohorts | Scale pathway credible | Iterate onboarding/offer | No paid usage or material risk | GTM / Sales | Not yet observed | Pending

## Evidence & Sources
M6.6 evidence inventory ¦ What is known versus hypothesized
Claim class | Evidence | Limitation | Source path / link | Evidence grade | Owner | Last checked | Data type
Completed local build | ChartGround M1–M5: API, metering, budget, invoicing simulation, dashboard; 151 offline tests | No paid customer, deployment or enterprise approval | ChartGround M1–M5 milestone log | Locally tested | Project | 2026-10-29 | Observed local
Market selection | Clinical workflow ISVs lead weighted M6.1 scorecard; oncology first specialty | Secondary research; overlapped categories and subjective weights | ChartGround_M6_1_Healthcare_Market_Selection_Analysis.xlsx | Analyst scored | M6.1 | 2026-10-29 | Research / hypothesis
Modeled billings | First-year $1.5K / $125.4K / $2.384M conservative/base/expansion | Assumed adoption, workflows, model mix, token sizes and discounts | ChartGround_M6_2_Healthcare_API_Monetization_Revenue_Model.xlsx | Model only | M6.2 | 2026-10-29 | Hypothesis
Developer funnel | M6.3 proposes first call -> evaluation -> pilot -> paying production | No observed external ISV conversion cohort | ChartGround_M6_3_Developer_Adoption_Funnel_and_Roadmap.xlsx | Proposed targets | M6.3 | 2026-10-29 | Hypothesis
Buyer landscape | 20 real researched companies; six discovery hypotheses | No outreach, buyer interest or Claude model adoption verified | ChartGround_M6_4_Healthcare_Target_Accounts_Enterprise_Readiness.xlsx | Public research | M6.4 | 2026-10-29 | Secondary research
Competition / partners | Citation feature and cloud distribution pathways; comparison benchmark required | No head-to-head current-model evaluation and no new signed partners | ChartGround_M6_5_Competitive_Positioning_Partner_Strategy.xlsx | Public research | M6.5 | 2026-10-29 | Secondary research
Native citation caveat | Claude citation blocks and strict structured outputs incompatible in same request | Architectural solution must be tested | https://platform.claude.com/docs/en/build-with-claude/citations | Official docs | Anthropic | 2026-10-29 | External
Deployment gate | Different BAA/channel and eligible-feature requirements apply | Must verify actual signed agreements and architecture | https://docs.aws.amazon.com/claude-platform/latest/userguide/cpa-vs-bedrock.html | Official docs | AWS | 2026-10-29 | External
Existing partner route | TCS / Anthropic regulated-industry partnership publicly announced | Does not constitute a ChartGround partner relationship | https://www.anthropic.com/news/tcs-anthropic-partnership | Official announcement | Anthropic | 2026-10-29 | External

## Executive Summary
M6.6 ¦ Executive decision dashboard
Decision lens | Key value | Interpretation | Evidence basis
M6.2 base year-1 API billings ($) | 125411.9363 | Illustrative adoption and consumption only
M6.2 base month-12 annualized ($) | 268849.0035 | Run rate, not realized year-one revenue
Illustrative scenario-weighted year-1 billings ($) | 164030.274 | 60%/35%/5% analyst weights; not empirical likelihoods
Downside-stressed base year-1 billings ($) | 84653.057 | 75% workflow × 90% realized price sensitivity
M6.2 $1M run-rate ISV equivalence | 186 | Assumes M6.2 base per-ISV intensity, not sales forecast
Investment stance | Authorization boundary | Validation gate
Approve now | Discovery, blinded evaluation, channel/security review | Named accountable owner; bounded capacity / Finance review
Withhold | Broad launch, reseller commitments, PHI deployment | No external buyer, validated performance or end-to-end approval yet
Day 90 decision | GO / ITERATE / STOP pilot funding | Based on interview, benchmark and economics evidence
Day 180 decision | Paid-production and sustained usage assessment | Only real production events—not ChartGround demos